## NPV
Net Present Value (NPV)
Created by |  | Date:
Discount rate | 8%
EPM | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Benefits | 0 | 3000 | 4500 | 6500 | 8500 | 10500
Costs | 7150 | 900 | 800 | 700 | 600 | 500
Cast flow | -7150 | 2100 | 3700 | 5800 | 7900 | 10000
NPV | 14058.6971

## Financial Analysis
Phân tích tài chính dự án EPM
Tạo bởi: |  | Ngày:
Discount rate | 8%
Assume the project is completed in Year 0 | Year
| 0 | 1 | 2 | 3 | 4 | 5 | Total
Costs | 7150 | 900 | 800 | 700 | 600 | 500 | 10650
Discount factor | 1 | 0.92593 | 0.85734 | 0.79383 | 0.73503 | 0.68058
Discounted costs | 7150 | 833.3333 | 685.8711 | 555.6826 | 441.0179 | 340.2916 | 10006.1965
Benefits | 0 | 3000 | 4500 | 6500 | 8500 | 10500 | 33000
Discount factor | 1 | 0.92593 | 0.85734 | 0.79383 | 0.73503 | 0.68058
Discounted benefits | 0 | 2777.7778 | 3858.0247 | 5159.9096 | 6247.7537 | 7146.1236 | 25189.5894
Discounted benefits - costs | -7150 | 1944.4444 | 3172.1536 | 4604.227 | 5806.7358 | 6805.832 | 15183.3929 | NPV
Cumulative benefits - costs | -7150 | -5205.5556 | -2033.4019 | 2570.8251 | 8377.5609 | 15183.3929
ROI(Return On Investment) | 151.7%
Payback before Year 3
Assumptions
Enter assumptions here

## Payback
Thời gian hoàn vốn của dự án EPM
Tạo bởi: |  | Ngày:
Year | Costs | Benefits | Cumulative Costs | Cumulative Benefits
0 | 7150 | 0 | 7150 | 0
1 | 900 | 3000 | 8050 | 3000
2 | 800 | 4500 | 8850 | 7500
3 | 700 | 6500 | 9550 | 14000
4 | 600 | 8500 | 10150 | 22500
5 | 500 | 10500 | 10650 | 33000
Payback

## Earned Value
Earned Value Calculations for EPM
Prepared by: |  |  | Date:
[6 empty] | To Date | Planned | Actual
Activity | Sep, 23rd 2009 | Oct | Nov | Dec | Jan | PV (Planned Value) | % Complete | % Complete | RV | EV (Earned Value)
Staff project and train business process | 2100 |  |  |  |  | 2100 | 100 | 100 | 100% | 2100
Technical training |  | 1100 |  |  |  | 1100 | 100 | 100 | 100% | 1100
Planning |  | 100 |  |  |  | 100 | 100 | 90 | 90% | 90
Analyze requirements |  | 350 |  |  |  | 350 | 100 | 100 | 100% | 350
Class Analyse and Diagram |  | 510 |  |  |  | 510 | 100 | 95 | 95% | 484.5
DB Design |  | 310 |  |  |  | 310 | 100 | 100 | 100% | 310
Design forms, reports, and queries |  | 500 | 200 |  |  | 700 | 90 | 90 | 100% | 700
Construct working prototype |  |  | 100 |  |  | 100 | 100 | 100 | 100% | 100
Technical document |  |  | 200 | 100 | 100 | 400 | 90 | 80 | 88.89% | 355.5556
User document |  |  |  | 250 | 200 | 450 | 90 | 80 | 88.89% | 400
Test system |  |  |  | 400 | 200 | 600 | 90 | 90 | 100% | 600
Review and evaluate |  |  |  | 160 |  | 160 | 100 | 90 | 90% | 144
Incorporate user feedback |  |  |  | 610 | 300 | 910 | 90 | 90 | 100% | 910
Train users |  |  |  | 320 | 200 | 520 | 90 | 90 | 100% | 520
Reflectiom (Cost report, Product evaluation, lessons learned) |  |  |  |  | 200 | 200 | 100 | 100 | 100% | 200
Maintenance |  |  |  |  | 400 | 400 | 90 | 90 | 100% | 400
[8 empty] | Total EV |  | 8764.0556
Monthly Planned Value (PV) | 2100 | 2870 | 500 | 1840 | 1600
Cumulative Planned Value (PV) | 2100 | 4970 | 5470 | 7310 | 8910
Monthly Actual Cost (AC) | 2200 | 3200 | 400 | 2500 | 750
Cumulative Actual Cost (AC) | 2200 | 5400 | 5800 | 8300 | 9050
Monthly Earned Value (EV) | 2100 | 3000 | 300 | 2000 | 2000
Cumulative Earned Value (EV) | 2100 | 5100 | 5400 | 7400 | 9400
Project EV as of JAN 13th | 8764.0556
Project PV as of JAN 13th | 8910
Project AC as of JAN 13th | 9050
CV (Cost Variance) = EV - AC | -285.9444
SV (Schedule Variance) = EV - PV | -145.9444
CPI (Cost Performance Index) = EV / AC | 96.84%
SPI (Schedule performance index) = EV / PV | 98.36%
Estimate at Completion (EAC) = BAC/CPI | 9200.7062 | (original plan of $8910 divided by CPI)
Estimated time to complete | 3.2838 | (original plan of 3.23 months divided by SPI)
Note: BAC = the budget at completion

## Cost Estimate
EPM Project Cost Estimate
Prepared by: | Date:
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 7605 | 24.98%
1.1 Project manager | 646 | 4 | 2584
1.2 Project team members | 2120 | 2 | 4240
Contractors (10% of software development and testing) |  |  | 781
2. Hardware |  |  |  | 3000 | 9.852%
2.1 Computer | 2000 | 1.5 | 3000
3. Software |  |  |  | 7100 | 23.32%
3.1 Licensed software | 100 | 3 | 300
3.2 Software development |  |  | 6800
4. Testing (10% of total hardware and software costs) |  |  | 1010 | 1010 | 3.317%
5. Training and Support |  |  |  | 6660 | 21.87%
5.1 Trainee cost | 150 | 4 | 600
5.2 Travel cost | 12 | 5 | 60
5.3 Project team members | 1500 | 4 | 6000
6. Reserves (20% of total estimate) |  |  | 5075 | 5075 | 16.67%
Total project cost estimate |  |  |  | 30450